## Sheet1
Component | Task | Must/Should/Could/Will not have for MVP
System | Complete migration to Azure VM
System | Design log files/system analytics
System | Automate with daily cron job
System | System dashboard: metrication of LitScan successes/failures and cost monitoring
System | Network: monitor TLS certificates (sometimes they expire and the system breaks!)
System | Agree BirdLife adoption route (LitScan is currently hosted in an isolated Azure subscription, which prevents BirdLife access to LitScan file shares) So a plan is needed on the expected resourcing for operational management of the tool. This in turn will affect requirements for the Azure architecture.
Scanner | Review Bing storage with Microsoft
Scanner | Review Google Scholar API and usage
Scanner | Add new sources in response to user requests (e.g. specific searching of Notornis, Ostritch and Kukila journal websites, and the abstract database Scopus. Possibly ResearchGate?). Enable Bing search through discussion with MicroSoft again. | M
Scanner | Monitor per-domain format and x-paths [ongoing]
Scanner | Expand non-English coverage (e.g. in partnership with Queensland team)
Scanner | Refine and improve the PDF processing (improve the abstract-parsing and tailoring it to particular document series) | S/C
Scanner | OpenAlex scan needs fixing in response to undiagnosed API changes
Scanner | Explore enabling scanning of the main text of papers behind paywalls for which we have access via affiliation to University of Cambridge (more generically, allowing user credentials to enable access to restricted content) | W but good to think through the possibilities here soon
Processing | Incorporate active learning loop to scoring
Processing | Add geo extraction and functionality
Processing | Explore use of DL-based text analysis and/or use of LLM for fine-grained information discovery
Web app | Fix PDF upload at the firewall (currently works up to AG) (i.e. functionality to allow assessors to upload pdfs of relevant reports and OBC/ABC/NBC journals and pre-assign relevance scores) | M
Web app | Move uploaded PDFs to static location in blitshare
Web app | Display citation info, not just title
Web app | Add feedback functionality (score, date initially) so assessors can confirm/correct the prioritisation ranking the algorithm generates, and develop the algorithm to integrate this feedback | S/C
Web app | Add translation toggle
Web app | Dashboard: refresh (database) dashboard design
Web app | Design & implement species view coupled to DataZone